## Milestones
S.No. | Name | Cost | Timing | Total Cost=2980
Milestone 1 | 1. Setup application on provided server 2. Registration and login for user 3. User profile --Display type of profile and others personal information 4. Rate profile 5. User management | 500 | 15 days
Milestone 2 | 1. Event Management, Payment management 2. Multi-Language setting -- It will be manage with application as the application will proceed to complete in each section 3. Live comments | 500 | 15 days
Milestone 3 | 1. Livestreaming Video functionality with third party Service | 500 | 15 days
Milestone 4 | 1. Livestreaming Video functionality with third party Service | 500 | 15 days
Milestone 5 | 1. search 2. Events Scheduling 3. Social Media Sharing 4. Payment gateway | 500 | 15 days
Milestone 6 | 1. Test and Bug fixing | 480 | 15 days