## Milestones
S.No. | Name | Timing
Milestone 1 | 1. Setup application on provided server 2. Registration and login for user 3. User profile --Display type of profile and others personal information 4. Rate profile 5. User management | 15 days
Milestone 2 | 1. Event Management, Payment management 2. Multi-Language setting -- It will be manage with application as the application will proceed to complete in each section 3. Live comments | 15 days
Milestone 3 | 1. Livestreaming Video functionality with third party Service | 15 days
Milestone 4 | 1. Livestreaming Video functionality with third party Service | 15 days
Milestone 5 | 1. search 2. Events Scheduling 3. Social Media Sharing 4. Payment gateway | 15 days
Milestone 6 | 1. Test and Bug fixing | 15 days

## Tasks per user
Normal User (Customers) | Search for upcoming events
Register
Login
Make Payment (Choose Package)
Registered Customer
Profile (View, update, Delete)
Check Package / Upgrade / Downgrade
Paid Events (upcoming and Past)
Search New upcoming Events and Make Payment
Attend Live Event
Comment during Live Event
Save Live Event
Contact Customer Service (by email)
Rate Performers
User Performers | Register
| Login | Registered Performers
Profile (View, update, Delete)
Check Package / Upgrade / Downgrade
Create / Schedule Live Event
Perform Live Event
Reply to comment
Save Performance
Contact Customer Service (email)
Check Rates and reply
Administrator Panel | Login
Complete Dashboard
Manage User
Create Staff (Super Admin, Agents)
User (Customer, performers) management (View, update, restricted)
Manage Event
Add new event, update/delete event for performers
Manage Payment
Paid Events
Refund Listing